## Sheet2
Machine Specifications
Safety Certification Label | N/A
Boom Hydraulic Check Valve | Yes
Adjustable Boom System | N/A
Automatic Lubrication System | N/A
Arm Hydraulic Check Valve | Yes
Diesel Particulate Filter | N/A
Hydraulic Hammer Lines | Yes
Grapple and Shear Hydraulic Lines | N/A
Diesel Exhaust Fluid System AddBlue | N/A
Stabilizer Blade Condition | N/A
Operator Cabin Details
Seat and Arm Support | Ok
Cab Doors and Covers | Ok
control levers, Control stick | Ok
Windows and Mirrors | Ok, No Mirrors
Dashboard Screen, Gauges and | Ok
Warning alarms message | Ok, climate system error message
Washer, Wipers | Ok
Air Conditioning and Heating System | Not Cooling
Cab Floor Covering | Ok
Cab Structure, Gard | Ok, No Guard
Electrical System | Ok
Engine & Performance
Electronic Fuel Injection System | Electronic
Engine Model | D13F
Engine Cooling System | Ok
Engine Oil Check | Ok
Exhaust System and Muffler | Normal
Belts and Air/Oil Filters | Ok
Warning alarms, messages | Normal
Coolant | ok
Coolant condition | Ok
Exterior Condition & Visual Inspection
Main Frame and Track Frame | Ok
Protective Covers and Sheets | Ok
Engine Hood | Ok
Side Access Doors | Ok
Steps and Handrails | Ok
Storage Compartments | Ok
Boom Condition | Ok
Bumpers and Catwalk Condition | Ok
Arm Condition | Ok
Lights | Ok, Need Wiring Joint
Battery Check | Ok
Exterior Paint Condition | Ok
Hydraulic System
Hydraulic Leaks | Minor oil leak from pump front gasket
Boom Hydraulic Jack | Ok
Hydraulic Pump and Valve Block | Functional
Bucket Hydraulic Jack | Ok
Arm Hydraulic Jack | Ok
Welded Components | Bucket Cylinder
Limited Functional Testing & Operation
Boom Pins Condition | Ok
Excavator self- Drift Test | Ok
Arm Pins Condition | Ok
Hydraulic Pump Noise Check | Ok, little noisy
Bucket Pins Condition | Need new bush, spacer, washer
Slewing Ring Bearing Movement Check | Ok, little loose
Swing Drive and Brake Test | Ok
Drive force Test | Ok
Attachments
Attachments model | digging bucket
Size | W1530, H1200, D1050 mm
Status | Ok
Coupler status | Ok
Second Attachments model | N/A
Size | N/A
Status | N/A
Undercarriage COMPONENT Remaining estimated LIFE
Bushings | 50%
Track shoes | 50%
Idlers | 50%
Shoe width in mm: | 600 mm
Track pitch in mm: | 80 mm
carrier rollers | 30%
Track rollers | 30%
Track links | 30%
Sprocket segments | 30%

## Sheet1
¦ | **Machine Overview** | ¦
¦ | Safety Certification Label | ¦
¦ | Boom Hydraulic Check Valve | ¦
¦ | Adjustable Boom System | ¦
¦ | Automatic Lubrication System | ¦
¦ | Stick Hydraulic Check Valve | ¦
¦ | Diesel Particulate Filter | ¦
¦ | Hydraulic Hammer Lines | ¦
¦ | Grapple and Shear Hydraulic Lines | ¦
¦ | Diesel Exhaust Fluid System | ¦
¦ | Stabilizer Blade Condition | ¦
¦ | Air Conditioning System | ¦
¦ | **Cab Interior Inspection** | ¦
¦ | Seat and Arm Support | ¦
¦ | Cab Doors and Covers | ¦
¦ | Control Switches and Joysticks | ¦
¦ | Windows and Mirrors | ¦
¦ | Dashboard Gauges and Warning Lights | ¦
s, | Washer ¦ Climate Control System and Wipers/Wa | sher ¦
¦ | Air Conditioning and Heating System | ¦
¦ | Cab Floor Covering | ¦
¦ | Cab Body Condition | ¦
¦ | **Engine Inspection** | ¦
¦ | Electronic Fuel Injection System (Model D13F) | ¦
¦ | Fluid Leaks and Seals | ¦
¦ | Engine Cooling System | ¦
¦ | Engine Oil Check | ¦
¦ | Engine Blow-by Check | ¦
¦ | Exhaust System and Muffler | ¦
¦ | Belts and Air/Oil Filters | ¦
¦ | Exhaust Smoke Analysis | ¦
¦ | Coolant Level and Quality | ¦
¦ | **Exterior Condition Check** | ¦
¦ | Main Frame and Track Frame | ¦
¦ | Protective Covers and Sheets | ¦
¦ | Engine Cover | ¦
¦ | Side Access Doors | ¦
¦ | Access Steps and Handrails | ¦
¦ | Storage Compartments | ¦
¦ | Boom Condition | ¦
¦ | Bumpers and Catwalk Condition | ¦
¦ | Stick Condition | ¦
¦ | Lights and Battery Check | ¦
¦ | Light Wiring Condition | ¦
¦ | Exterior Paint Condition | ¦
¦ | **Hydraulic System Check** | ¦
¦ | Hydraulic Hoses, Lines, and Swivel Joints | ¦
¦ | Boom Hydraulic Cylinders | ¦
¦ | Hydraulic Pump and Valve Block | ¦
ke | t ¦ Hydraulic Pump Gasket Leak | ¦
¦ | Stick Hydraulic Cylinder | ¦
¦ | Bucket Hydraulic Cylinder | ¦
¦ | Welded Components | ¦
¦ | **Operational Test** | ¦
¦ | Boom Pins Condition | ¦
¦ | Boom Drift Test | ¦
¦ | Stick Pins Condition | ¦
¦ | Hydraulic Pump Noise Check | ¦
¦ | Bucket Pins Condition | ¦
¦ | Slew Ring Movement Check | ¦
¦ | Swing Drive and Brake Test | ¦
¦ | Electrical System Check | ¦
¦ | Drive Train Test | ¦
¦ | **Tool Inspection** | ¦
¦ | Bucket 1 Size and Type | ¦
¦ | Bucket 2 Size and Type | ¦
¦ | Tool Condition | ¦
¦ | Coupler Condition | ¦
s | implified naming convention for better underst | anding and readability. Let me know if you need further adjustments!